## Hoja 1
Phase | Activities | Responsible | Effort (hrs) | Notes | Observations | SEMANA 1 | SEMANA 2 | SEMANA 3 | SEMANA 4 | SEMANA 5 | SEMANA 6
Initial Setup and Kickoff | Account creation and/or configuration |  | 2
| Creating and configuring network resources |  | 3
| Definition of integration tests of the complete application |  | 3
| Documentation |  | 2
Migrating application servers from IBM account to AWS account | Definition of Dates and Schedule for IBM Application Servers Migration |  | 3
| Application Migration Service Configuration in target AWS account |  | 3
| Installation Replication Agent on Application Servers |  | 2
| Replication Phase by Application Migration Service to AWS |  | 15
| Documentation |  | 4
Migrating database servers from IBM account to AWS account | Generating and uploading DB Backup from DB Servers to AWS S3 in target account |  | 4
| Create/Configure RDS target Instances |  | 4
| Load Backup into RDS Target Instances |  | 4
| Create/Configure CDC DMS replications task |  | 3
| Enable replication between IBM source Database and RDS target Database |  | 4
| Documentation |  | 2
Application Configuration and Database Connections in AWS Account | Launch/Check Test Instances in AWS Account for Peru Server |  | 2
| Perform Tests to validate Migration |  | 4
| Terminate Test Instances and Launch/Check Cutover Instances |  | 2
| Perform Configuration and Connections to Resources in AWS Account |  | 4
| Perform Tests to validate service funcionality |  | 4
| Launch/Check Test Instances in AWS Account for Paises V1 - Paises V2 Server |  | 2
| Perform Tests to validate Migration |  | 4
| Terminate Test Instances and Launch/Check Cutover Instances |  | 2
| Perform Configuration and Connections to Resources in AWS Account |  | 10
| Perform Tests to validate service funcionality |  | 6
| Launch/Check Test Instances in AWS Account for API Global |  | 2
| Perform Tests to validate Migration |  | 4
| Terminate Test Instances and Launch/Check Cutover Instances |  | 2
| Perform Configuration and Connections to Resources in AWS Account |  | 6
| Perform Tests to validate service funcionality |  | 4
| Launch/Check Test Instances in AWS Account for Frontend |  | 2
| Perform Tests to validate Migration |  | 4
| Terminate Test Instances and Launch/Check Cutover Instances |  | 2
| Perform Configuration and Connections to Resources in AWS Account |  | 6
| Perform Tests to validate service funcionality |  | 4
| Documentation |  | 2
Elastic Load Balancing Creation/Configuration / CloudFront Creation/Configuration / CloudWatch Monitoring Configuration | Creation/Configuration Cloudfront Distributions |  | 4
| CloudFront association to Application Load Balancers |  | 4
| Creation/Configuration Application Load Balancers in AWS Account |  | 2
| Creation/Configuration Target Groups |  | 2
| Creation SSL/TLS Certificates in AWS Certificate Manager |  | 2
| Installation/Configuration CloudWatch Agent on AWS EC2 Servers |  | 4
| Creation Alarms/Dashboards with Critical Metrics for Monitoring |  | 6
| Creation/Configuration SNS Topics for Alarms Notifications for Turismoi Team |  | 3
| Installation/Configuration SSM Agent on AWS EC2 Servers |  | 4
| Documentation |  | 4
Traffic redirection to infrastructure from IBM to AWS | Complete application integration testing |  | 6
| DNS Hosted Zone Route53 Creation |  | 4
| DNS Hosted Zone Route53 Traffic Routing |  | 4
| Infrastructure shutdown in IBM Cloud |  | 8
| Documentation |  | 2
Migration Closure Configuration | Validation of working production application and closure presentation |  | 10
| Documentation |  | 2
Training | Migration closure documentation |  | 4
| Training on the operation of the application and services |  | 5
216